Proposed changes to the RF

1. Structural changes

* Change the numbering format, especially for activities and PIs, for enhanced ease of flow. E.g PI 1 for activity 2 under output 3, should be labelled as PI 3.2.1
* Reduce/ combine Activity PIs to reduce redudancy

1. Content changes

Impact

General Comment: Revise to reflect high-level impact. E.g, number of lives/livelihoods, property impacted/saved. E.g., along country coastlines

**Impact: Enhance t**he resilience and adaptive capacity of coastal communities in Kenya, Mozambique, Seychelles, and Madagascar by equipping policymakers, institutions, and researchers with reliable, accessible, and actionable sea-level data and information

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PI 2. Proportion of coastal communities and/or institutions in Kenya, Mozambique, Seychelles, and Madagascar reporting improved preparedness and adaptation based on the use of project-supported sea-level data | N/a |  | No of communities institutions using sea-level data to develop preparedness strategies | 25% | 50 % | At least 50 % |
| PI 3. No of sea level data-informed policy briefs developed directly as a result of the project | 0 |  | Count of the number of policy briefs developed | 0 | 1 | 4 (1 per country) |

**Outcome**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PI 1. Number of institutions engaged in capacity development initiatives | 4 | IOCAFRICA Session reports | Quarterly reports | 6 | 6 | 12 |
| PI 2 Number of sea-level monitoring stations consistently producing accessible data to inform evidence-based policy and decision making | 0 | IOCAFRICA Survey (2021-2022)  GLOSS Reports | Annual reports | 9 | 19 | 19 |

This number can be aligned with the stakeholder mapping exercise

**Output N°3 Development and deployment of interoperable sea-level data management systems at national levels**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PI 2. Number of data entries and national databases added and linked to the Regional ODIS Node | 0 | National reports -2023 | Number of new databases | 4 | 4 | 4 |  |

Action: Revise the entire PI list for output 3 since the project won’t be developing databases

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Output N°4: Delivery of targeted training programs and capacity-building workshops** | | | | | | | |
| PI 1. Number of training sessions , and / or university courses, undertaken within the four beneficiary countries | 2 | IOCAFRICA Session reports | Reports of successful training events | 1 | 1 | 2 |